## 10-05-2012
| Removed from existing | New design | Comments by Pavan | Comments by Manoj | Responses | Call updates
Summary
1 | "Available Now" field was removed | New fields: Expected salary From and To drop downs. |  | Need to have available now | Ok
2 | Save button removed from section and moved to the bottom of the page, which may save entire page changes. |  |  | Save button need for each section to save individually | Both should be there
Experience - current
1 | Period field was removed | Period made into two parts. From and To. | Need to change the db structure to store these values | no need to change period it is fine as of the current design | If this is correct, how can you show the duration of the experience in the VisualCV page. We have to show like '2 year 8 months' for each experience. | No change required
2 |  | Level, new drop down | What does this means? Provide values in the drop down? | Level field is used to plot the graph | What are the values? | Values will be given later. For now we take 1, 2,3..etc
3 |  | Industry and Skill were made as drop downs intead of text boxes. | We may need to create new tables for this! Provide values? Why these are not multi selected? | no need to change period it is fine as of the current design | The question is for skill not for period. | No need to change
4 |  | Achievements, Portfolios & Videos are newly added | We may need to create new tables for this! | Yes this to be done | Ok | Needs to come up with new tables | Need to generate feed(adding an event log) will be shown in someother module. Yet to finalize the tables fromManoj.
Experience - past
1 | Period field was removed | Period made into two parts. From and To. | Need to change the db structure to store these values | no need to change period it is fine as of the current design | If this is correct, how can you show the duration of the experience in the VisualCV page. We have to show like '2 year 8 months' for each experience.
2 |  | Level, new drop down | What does this means? Provide data to be here in the drop down? |  | What are the values?
3 |  | Industry and Skill were made as drop downs intead of text boxes. | We may need to create new tables for this! What could be the data in this tables? Why these are not multi selected? | no need to change period it is fine as of the current design | The question is for skill not for period.
4 |  | Achievements, Portfolios & Videos are newly added | We may need to create new tables for this! |  | I think we have to store in files DB. | same as above
Education
1 | Period field was removed | Included Year, from and To fields | Need to change the db structure to store these values | no need to change period it is fine as of the current design | Ok | no need to change
School
1 | Period field was removed | Included Year, from and To fields | Need to change the db structure to store these values | no need to change period it is fine as of the current design | Ok | no need to change
Contact details
1 | Order of the fields were changed |  |  | no need to change | Ok | no need to change
2 | Email lable got changed to "Alternative Email" |  |  |  |  | no need to change
3 |  | Web site, blog, city, country, Maritial status newly added | I think, Home address fields should be moved above to City fields? Is country list available in the DB or need to create new? | Already we are having those fields no need to do | So you are saying we have these fields in DB but not in UI. So we have to change the UI by including the fields. Am I right? | no need to change
Common section
1 |  | This is a new section | I think section is incomplete? | ignore | Ok | no need to change
General
1 |  | Add language button | What is the functionality here? Do we need to open a popup? | languages known should be changed to auto complete box.Whn add a language a is clicked it should opena tab and have atextbox to save the new language | I think language known is a rgular text box. User is free to enter anything. And add language is provided to enter other languages, so we add that section again when user clicks on it. This would be better, what do you say? | Need to get confirmation from client for Add button. My view is to add new language to the user but not to the master data base. | We need to create new table for language, interest, skill. We may need to drop existing columns | Button click wil add new set and user can enter another language.
2 |  | Add Interest button | What is the functionality here? Do we need to open a popup? | same as above | same as above? |  |  | Button click wil add new set and user can enter another language.
3 |  | Add skill buttom | What is the functionality here? Do we need to open a popup? | Should be conveerted into autocomplete box with one character.Add skill should open a tab with textbox to enter the skill | same as above? |  |  | Button click wil add new set and user can enter another language. | If user enters a skill not in the DB we have to add it to the DB and save user selection
4 |  | How long | is this as drop down or text? Text would be recommended. | This has to drop down with years(<1,<2…10> | how can we ristrict it to till 10? | understood manoj comments
5 |  | Expected salary | I think field got repeated. We have the same in the Summary section | ignore the summary section | Ok | no need to implement
6 | Skill |  | Moved to common section | no need to change | Ok | no need to implement
7 | Company logo |  | Moved to common section | no need to change | OK | no need to implement
8 | Avalaible now | in visual cv we need to have a small grey tab as that of the position looking for.If the user ticks in edit we show yes otherwise no |  |  | You mean "Position looking for" box? | Need to have grey box similar to Position looking for in the Visual CV. Between Position looking for and salary from. If in edit profile checked avaialable now then we show Yes here. If not No