## List of pages
S.no | Page Names | Status | Developer | Target date | Notes | Page links | S.no | Major Functionalties | Status | Developers | Target date
1 | Article |  |  |  |  | http://huntable.co.uk/article.aspx | 1 | Freezing in Entire Huntable
2 | Article view |  |  |  |  | http://huntable.co.uk/articleview.aspx | 2 | Message Popup opening
3 | Business Activity |  |  |  |  | http://huntable.co.uk/Businessactivity.aspx | 3 | Phase 1 Ammnedemnets
4 | Employee Activity |  |  |  |  | http://huntable.co.uk/Employeeactivity.aspx | 4 | Yahoo invitations
6 | Carrer-Jobs in huntable |  |  |  |  | http://huntable.co.uk/companyjobs.aspx
7 | Companies-jobs available |  |  |  |  | http://huntable.co.uk/companiesjobs.aspx
8 | Companies-country |  |  |  |  | http://huntable.co.uk/companiescountry.aspx
9 | Company-follower |  |  |  |  | http://huntable.co.uk/companiesfollowers.aspx
10 | Company-industry |  |  |  |  | http://huntable.co.uk/companieshome.aspx
11 | Company-Size |  |  |  |  | http://huntable.co.uk/companiessize.aspx
12 | User-Companies |  |  |  |  | http://huntable.co.uk/companies.aspx
13 | Company-BLogs1 |  |  |  |  | http://huntable.co.uk/company-blogs-popular.aspx
14 | Company-Blogs2 |  |  |  |  | http://huntable.co.uk/companyblogsrecent.aspx
15 | Company-products |  |  |  |  | http://huntable.co.uk/companyproducts.aspx
16 | Company-Registration Home | Start on 21-11-2012 | Manoj |  |  | http://huntable.co.uk/company-registration.aspx
17 | Company-registration1 | start on 22-11-2012 | Manoj |  |  | http://huntable.co.uk/companyregistration2.aspx
18 | Company-registration2 | start on 23-11-2012 | Manoj |  |  | http://huntable.co.uk/companyregistration3.aspx
19 | Comopany view |  |  |  |  | http://huntable.co.uk/companyview.aspx
20 | Customized Invitation | Need to assign to kalyan |  |  |  | http://huntable.co.uk/customizedinvitation.aspx
21 | Likes |  |  |  |  | http://huntable.co.uk/Likes.aspx
22 | See more recuirters | Alaphabetical search yet to work | Narasimha |  |  | http://huntable.co.uk/SeeMoreRecruiter.aspx
23 | Super power profile | Completed | Narasimha |  |  | http://huntable.co.uk/Super-power.aspx
24 | Videos | Start on 21-11-2012 | Satish | 22-11-2012 | This page has networking concepts | http://huntable.co.uk/videos.aspx
25 | Visual Cv Activity |  |  |  |  | http://huntable.co.uk/visualcvactivity.aspx
27 | Home page Tour | Arun's review | Manoj |  |  | http://huntable.co.uk/HomePageTour.aspx
28 | Home page-Jobs in feed | Arun's review | Manoj |  |  | http://huntable.co.uk/HomePageAfterLoggingIn.aspx
29 | Companies home |  |  |  |  | http://huntable.co.uk/companieshome.aspx
30 | Companies Country |  |  |  |  | http://huntable.co.uk/companiescountry.aspx
31 | Companies Products |  |  |  |  | http://huntable.co.uk/companyproducts.aspx
33 | companies-size |  |  |  |  | http://huntable.co.uk/companiessize.aspx
34 | Companies followers |  |  |  |  | http://huntable.co.uk/companiesfollowers.aspx
35 | Companies-blog1 | start on 23-11-2012 | Narasimha |  |  | http://huntable.co.uk/company-blogs-popular.aspx
36 | Companies-blog2 | start on 23-11-2012 | Satish |  |  | http://huntable.co.uk/companyblogsrecent.aspx
37 | Companies-view |  |  |  |  | http://huntable.co.uk/companyview.aspx
38 | Networking | Yet to start | Komal
39 | Pictures | Start on 21-11-2012 | Narasimha | 22-112012 | This page has networking concepts | http://huntable.co.uk/pictures.aspx
40 | Followers | Arun's review | Manoj |  |  | http://huntable.co.uk/Followers.aspx
43 | Visual Cv |  | Pavan |  |  | http://huntable.co.uk/visualcv.aspx
44 | Companiesyoumaywantto follow | Arun's review | Satish |  |  | http://huntable.co.uk/Companiesyoumaywant.aspx
45 | Following | Arun's review | Satish |  |  | http://huntable.co.uk/Following.aspx

## Sheet1
S NO | PAGE NAME | DESIGN STATUS | DESIGN DEVELOPER | CODING STATUS | CODE DEVELOPER | Target Dates | LIVE LINKS | COMMENTS
1 | LIKES | COMPLETED | AYYAPA BABU K |  |  |  | http://huntable.co.uk/likes.aspx
2 | COMPANY TO FOLLOW | COMPLETED | SATISH CH | Databasebase to be modified | Satish | 16-10-2012 | http://huntable.co.uk/companiesyoumaywant.aspx
3 | COMPANIES | COMPLETED | AYYAPA BABU K |  |  |  | http://huntable.co.uk/companies.aspx
4 | SEE MORE RECRUITER | COMPLETED | NARASIMHA CH | Alphabetical search remaining | Narasimha | 16-10-2012 | http://huntable.co.uk/seemorerecruiter.aspx
5 | SUPER POWER | COMPLETED | AYYAPA BABU K | Completed | Narasimha | Done | http://huntable.co.uk/super-power.aspx
6 | COMPANY BLOGS POPULAR | COMPLETED | AYYAPA BABU K |  |  | Yet to Assign | http://huntable.co.uk/company-blogs-popular.aspx
7 | EMAIL CONFIRMATION | COMPLETED | AYYAPA BABU K |  |  | Yet to Assign | http://huntable.co.uk/emailconfirmationsentsuccess.aspx
8 | EMAIL TEMPLATE | COMPLETED | AYYAPA BABU K |  |  | Linked to Companies | http://huntable.co.uk/emailtemplateeditpage.aspx
9 | VISUAL CV | PARTIALLY | PAVAN | Partially | Pavan | Not Given target date
10 | VISUAL CV TEXT | PARTIALLY | PAVAN
11 | COMPANY JOBS | COMPLETED | SATISH CH |  |  | Yet to Assign | http://huntable.co.uk/companyjobs.aspx
12 | HOME PAGE TOUR | Completed | NARASIMHA CH | Completed | Manoj | Completed | http://huntable.co.uk/HomePageTour.aspx
13 | JOBS IN FEED PAGE | Partially | Manoj | Completed | MAnoj | 16-10-2012 | http://huntable.co.uk/homepageafterloggingin.aspx
17 | COMPANIES | Completed | NARASIMHA CH |  |  | Yet to assign | http://huntable.co.uk/companies.aspx
18 | COMPANY MAP VIEW | Completed | NARASIMHA CH |  |  | Yet to assign | http://huntable.co.uk/companieshome.aspx
19 | COMPANY OVERVIEW(BA) | Completed | SATISH CH |  |  | Yet to assign | http://huntable.co.uk/BusinessActivity.aspx
20 | COMPANY OVERVIEW2(EA) | Completed | SATISH CH |  |  | Yet to assign | http://huntable.co.uk/EmployeeActivity.aspx
21 | COMPANY PRODUCTS | Completed | NARASIMHA CH |  |  | Yet to assign | http://huntable.co.uk/companyproducts.aspx
22 | COMPANY CARRERS | completed | NARASIMHA CH |  |  | Yet to assign | http://huntable.co.uk/carrers.aspx
23 | COMPANY BLOG RECENT | COMPLETED | NARASIMHA CH |  |  | Yet to assign | http://huntable.co.uk/companyblogsrecent.aspx
28 | COMPANY REG 2 | Completed | NARASIMHA CH |  |  | yet to assign | http://huntable.co.uk/CompanyRegistration2.aspx
30 | SHEET23(Company Edit) | Completed | NARASIMHA CH |  |  | yet to assign | http://huntable.co.uk/CompanyRegistration3.aspx
31 | COMPANY VIEW | Completed | NARASIMHA CH |  |  | yet to assign | http://huntable.co.uk/ComapnyView.aspx
32 | COMPANY REGISTRATION | PARTIALLY | SATISH CH |  |  | yet to assign | http://huntable.co.uk/company-registration.aspx
34 | NETWORKING | Given to Komal | Komal | Assigned To komal | Komal | 60 days
36 | Visual CV ACTIVITY | Completed | NARASIMHA CH |  |  | yet to assign | http://huntable.co.uk/VIsualCvActivity.aspx
37 | PICTURES | Completed | NARASIMHA CH |  |  | linked with edit profile | http://huntable.co.uk/Pictures.aspx
38 | VIEW PICTURES | Need find the scope
40 | FOLLOWERS | COMPLETED | SATISH CH | Completed | Manoj | 16-10-2012 | http://huntable.co.uk/followers.aspx
41 | VIDEOS | COMPLETED | NARASIMHA CH |  |  | linked with edit profile | http://huntable.co.uk/videos.aspx
42 | CUSTOMIZED INVITATION | COMPLETED | NARASIMHA CH |  |  |  | http://huntable.co.uk/customizedinvitation.aspx
44 | CUSTOMIZED FEEDS | Included in super profile | NARASIMHA CH | Completed | Narasimha | Completed | http://
45 | FOLLOW | Included in super profile | NARASIMHA CH | Completed | Narasimha | Completed
46 | CONNECT AND NETWORK | Included in super profile | NARASIMHA CH | Completed | Narasimha | Completed
47 | GET HUNTED | Included in super profile | NARASIMHA CH | Completed | Narasimha | Completed
48 | FIND JOB | Included in super profile | NARASIMHA CH | Completed | Narasimha | Completed
49 | PROMOTE COMPANY | Included in super profile | NARASIMHA CH | Completed | Narasimha | Completed
50 | OUR AIM | Included in super profile | NARASIMHA CH | Completed | Narasimha | Completed
51 | INVITE FRIENDSNEW | COMPLETED | NARASIMHA CH |  |  |  | http://huntable.co.uk/invitefriendsnew.aspx
52 | COMPANIES SIZE | COMPLETED | SATISH CH |  |  | Yet to Assign | http://huntable.co.uk/companiessize.aspx
53 | COMPANIES HOME | COMPLETED | SATISH CH |  |  | yet to assign | http://huntable.co.uk/companieshome.aspx
54 | COMPANIES FOLLOWERS | COMPLETED | SATISH CH |  |  | yet to assign | http://huntable.co.uk/companiesfollowers.aspx
Other Issues Working
| Freezing of header | Narasimham | [5 empty] | Waiting for client to finalize list
| Message Pop up Alerts | Manoj |  | Going on
| Phase1 Ammendments | [6 empty] | Yet to start