## List of pages
S.no | Page Names | Status | Developer | Target date | Notes | Page links | S.no | Major Functionalties | Status | Developers | Target date
1 | Article | BugsStage | Satish |  |  | http://huntable.co.uk/article.aspx | 1 | Freezing in Entire Huntable | Completed
2 | Article view | Bugs stage | Satish |  |  | http://huntable.co.uk/articleview.aspx | 2 | Message Popup opening | 50% completed | Pratusha
3 | Business Activity | Development | Komal |  |  | http://huntable.co.uk/Businessactivity.aspx | 3 | Phase 1 Ammnedemnets | 80% completed
4 | Employee Activity | Development | Komal |  |  | http://huntable.co.uk/Employeeactivity.aspx | 4 | Yahoo invitations
6 | Carrer-Jobs in huntable | Review stage | Narasimha |  |  | http://huntable.co.uk/companyjobs.aspx
7 | Companies-jobs available | Review Stage | Narasimha |  |  | http://huntable.co.uk/companiesjobs.aspx
8 | Companies-country | Review stage | manoj |  |  | http://huntable.co.uk/companiescountry.aspx
9 | Company-follower | Review Stage | Narasimha |  |  | http://huntable.co.uk/companiesfollowers.aspx
10 | Company-industry | Review stage | Satish |  |  | http://huntable.co.uk/companieshome.aspx
11 | Company-Size | Review Stage | Manoj |  |  | http://huntable.co.uk/companiessize.aspx
12 | User-Companies | Review Stage | Manoj |  |  | http://huntable.co.uk/companies.aspx
15 | Company-products | Review stage | Satish |  |  | http://huntable.co.uk/companyproducts.aspx
16 | Company-Registration Home | Bugs stage | Manoj |  |  | http://huntable.co.uk/company-registration.aspx
17 | Company-registration1 | Buigs stage | Manoj |  |  | http://huntable.co.uk/companyregistration2.aspx
18 | Company-registration2 | Bugs stage | Manoj |  |  | http://huntable.co.uk/companyregistration3.aspx
19 | Comopany view | Review stage | Narasimha |  |  | http://huntable.co.uk/companyview.aspx
20 | Customized Invitation | Development |  |  |  | http://huntable.co.uk/customizedinvitation.aspx
21 | Likes | Development |  |  |  | http://huntable.co.uk/Likes.aspx
22 | See more recuirters | Bugs stage | Narasimha |  |  | http://huntable.co.uk/SeeMoreRecruiter.aspx
23 | Super power profile | Completed | Narasimha |  |  | http://huntable.co.uk/Super-power.aspx
24 | Videos | Review stage | Satish | 22-11-2012 | This page has networking concepts | http://huntable.co.uk/videos.aspx
25 | Visual Cv Activity | Development | Komal |  |  | http://huntable.co.uk/visualcvactivity.aspx
27 | Home page Tour | Completed | Manoj |  |  | http://huntable.co.uk/HomePageTour.aspx
28 | Home page-Jobs in feed | Completed | Manoj |  |  | http://huntable.co.uk/HomePageAfterLoggingIn.aspx
35 | Companies-blog1 | Bugs stage | Narasimha |  |  | http://huntable.co.uk/company-blogs-popular.aspx
36 | Companies-blog2 | Review stage | Satish |  |  | http://huntable.co.uk/companyblogsrecent.aspx
37 | Companies-view | Bugs stage | Pratusha | 2012-02-12 |  | http://huntable.co.uk/companyview.aspx
38 | Networking | Development | Komal
39 | Pictures | Bugs stage | Narasimha | 22-112012 | This page has networking concepts | http://huntable.co.uk/pictures.aspx
40 | Followers | Review stage | Manoj |  |  | http://huntable.co.uk/Followers.aspx
43 | Visual Cv | Bug stage | Pavan |  |  | http://huntable.co.uk/visualcv.aspx
44 | Companiesyoumaywantto follow | Arun's review | Satish |  |  | http://huntable.co.uk/Companiesyoumaywant.aspx
45 | Following | Arun's review | Satish |  |  | http://huntable.co.uk/Following.aspx

## Huntable
Page Name or Functionality | Effort(In hours) | Completed | ETA

## People
| Manoj | Narasimha | Satish | Sravanthi | Tejaswi | Pratyusha | Komal | Pavan | Kavitha | Srihari
2012-11-19 | Preparing project plan | Home Page tour,Freezing | Jobs in Feed page,Freezing | Training Task | Training Task
2012-11-20 | Database for Companies | Freezing completion | Freezing completion | Training Task | Training Task |  | Client Review
2012-11-21 | Companies Registration page | Pictures | Videos | Training Task | Training Task |  | Database design
2012-11-22 | Companies Registration page | Pictures | Videos | Training Task | Training Task |  | Database design
2012-11-23 | Companies Registration page2 | Companies blog1 | Companies blog2 | Training Task | Phase1 amendments
2012-11-24 | See more recuiter alphabetical search | Companies blog1 | Companies blog2 | Training Task | Phase1 amendments
2012-11-26 | Preparing project plan | leave | Company registration patch | entity framework | entity framework
2012-11-27 | A-Z search,Add Pictures,videos user control | Company follower | Company products | entity framework | entity framework,Integration of links
2012-11-28 | User-Companies | Company-follower | Company products | Back up | Email templates huntable
2012-11-29 | Companies-country | Article view | Company idustry | leave | Email templates huntable
2012-11-30 | Company-size | Article view | company industry | leave | Slider in invite friends page
2012-12-01 | Company jobs available | Company carrers available | Followers user control | leave | Share concept in home page
2012-12-03 | Company jobs available | Company carrers available,Bugs | Companies you may be intersted in | Bd7 work | Share concept in home page
2012-12-04 | A-Z search | Add pictures user control | Companies you may be intersted in |  | Slider in invite friends page
2012-12-05 | A-Z search,bottom footer control | Add pictures user control | Portfolio java script |  | Java scripts learning
2012-12-06 | Companies login | Previous pages bugs | Portfolio java script |  | Java scripts learning
2012-12-07 | Companies login | Previous pages bugs | Previous pages bugs |  | Mvc 4 learning
2012-12-08 | Flow for webiste | Previous pages bugs | Previous pages bugs |  | Mvc 4 learning
2012-12-10
2012-12-11
2012-12-12
2012-12-13
2012-12-14
2012-12-15

## Weekly deliveries
2012-11-24 | 2012-12-01 | 2012-12-01 | 2012-12-08 | 2012-12-15 | 2012-12-22 | 2012-12-29
Freezing,HomePageTour,Followers,Following,Jobs in Feed Page,Company registration page,company registration2,Phase1 ammendments