## Project Tracker
Huntable Phase3 Tracking
|  |  | Percent Over/Under to Flag: | 25%
[5 empty] | in hours | in days
Task Name | Task Description | Assigned To | Est. Start | Est. Finish | Est. Work | Est. Duration | PROGRESS | Actual Start | Actual Finish | Actual Work | Actual Duration | Notes
T1 | Urls Changing | Narasimham | 2013-04-24 | 2013-04-26 | 9 | 2 | NOT STARTED |  |  |  | 0
T2 | Job Application popup | Narasimham | 2013-03-16 | 2013-03-16 | 7 | 0 | IN PROGRESS |  |  |  | 0 | bug fixing
T3 | Upload profile Page | Narasimham | 2013-03-18 | 2013-03-18 | 8 | 0 | ON ARUN's NAME |  |  |  | 0 | Aruns review
T4 | profiel Page popup | Narasimham | 2013-03-26 | 2013-03-26 | 7 | 0 | COMPLETED |  |  |  | 0 | Aruns review
T5 | Kalyans work | Kalyan | 2013-03-19 | 2013-04-29 | 0 | 40 | IN PROGRESS |  |  |  | 0 | Still working
T6 | Adapters for country | Narasimham | 2013-04-28 | 2013-04-29 | 16 | 1 | NOT STARTED |  |  |  | 0
T7 | Confirmation Popup | Narasimham | 2013-04-27 | 2013-04-27 | 6 | 0 | NOT STARTED |  |  |  | 0
T8 | Automatic Invoice | Manoj | 2013-03-23 | 2013-03-24 | 8 | 1 | ON ARUN's NAME |  |  |  | 0 | Completed
T9 | Alert Bell | Komal | 2013-03-18 | 2013-03-21 |  | 3 | IN PROGRESS |  |  |  | 0 | Completed
T10 | Upgrade email | manoj | 2013-03-26 | 2013-03-26 | 3 | 0 | ON ARUN's NAME |  |  |  | 0 | Completed
T11 | password change | manoj | 2013-03-27 | 2013-03-27 | 5 | 0 | ON ARUN's NAME |  |  |  | 0 | Completed
T12 | Email change | Narasimham | 2013-03-27 | 2013-03-27 | 8 | 0 | ON ARUN's NAME |  |  |  | 0 | Aruns review
T13 | Remainder Email | Narasimham | 2013-03-28 | 2013-03-29 | 9 | 1 | ON ARUN's NAME |  |  |  | 0 | Completed
T14 | Profile Zooming | Narasimham | 2013-03-30 | 2013-03-30 | 3 | 0 | IN PROGRESS |  |  |  | 0 | bug fixing
T15 | Edit Profile |  |  |  |  | 0 | NOT STARTED |  |  |  | 0
T16 | Delete Feeds | Komal |  |  |  | 0 | NOT STARTED |  |  |  | 0 | Working
T17 | Endorsement page | Narasimham | 2013-03-31 | 2013-04-01 | 11 | 1 | IN PROGRESS |  |  |  | 0
T18 | Block Button | Narasimham | 2013-04-02 | 2013-04-02 | 4 | 0 | ON ARUN's NAME |  |  |  | 0 | Completed
t19 | Remainder Email for jobs | Narasimham | 2013-04-05 | 2013-04-05 | 6 | 0 | ON ARUN's NAME |  |  |  | 0 | Completed
t20 | Visual Cv dispalyed | Narasimham | 2013-04-06 | 2013-04-06 | 7 | 0 | IN PROGRESS |  |  |  | 0 | Aruns review
t21 | Skill Search | manoj | 2013-04-01 | 2013-04-01 | 4 | 0 | NOT STARTED |  |  |  | 0 | Blocked
t22 | post Jobs Images | Narasimham | 2013-04-07 | 2013-04-08 | 12 | 1 | ON ARUN's NAME |  |  |  | 0 | bug fixing
T23 | people you want to follow | manoj | 2013-04-05 | 2013-04-06 | 12 | 1 | NOT STARTED |  |  |  | 0
T24 | Search before logging in | manoj | 2013-04-08 | 2013-04-08 | 6 | 0 | IN PROGRESS |  |  |  | 0
T25 | Company sends invitation | manoj |  |  |  | 0 | NOT STARTED |  |  |  | 0
T26 | Company recuirters login | Narasimham | 2013-04-16 | 2013-04-17 | 11 | 1 | STARTED |  |  |  | 0
T27 | Comments | Komal |  |  |  | 0 | ON ARUN's NAME |  |  |  | 0
T28 | Customized job is posted | Manoj | 2013-04-09 | 2013-04-09 | 6 | 0 | ON ARUN's NAME |  |  |  | 0
t29 | A user can start free company | Narasimham | 2013-04-18 | 2013-04-18 | 1 | 0 | NOT STARTED |  |  |  | 0
t30 | 10 free jobs | Narasimham | 2013-04-19 | 2013-04-19 | 2 | 0 | NOT STARTED |  |  |  | 0
t31 | Photo Reducing software |  |  |  |  | 0 | ON ARUN's NAME |  |  |  | 0
t32 | Our own advt | Narasimham | 2013-04-12 | 2013-04-13 | 12 | 1 | ON ARUN's NAME |  |  |  | 0 | Aruns review
t33 | Email Invitations | Kalyan |  |  |  | 0 | NOT STARTED |  |  |  | 0
t34 | Authorizing social networks | Kalyan |  |  |  | 0 | IN PROGRESS |  |  |  | 0
t35 | Chatsoftware | Srihari |  |  |  | 0 | NOT STARTED |  |  |  | 0
t36 | paypal | Srihari |  |  |  | 0 | IN PROGRESS |  |  |  | 0
T37 | refresh in people you may folow | manoj |  |  |  | 0 | NOT STARTED |  |  |  | 0
T38 | Secure page logic update | Narasimham | 2013-04-20 | 2013-04-20 |  | 0 | NOT STARTED |  |  |  | 0
T39 | Column in database field | Narasimham | 2013-04-22 | 2013-04-22 |  | 0 | NOT STARTED |  |  |  | 0
T40 | people you want to follow | manoj |  |  |  | 0 | NOT STARTED |  |  |  | 0
T41 | Affilate Patner | Narasimham | 2013-04-23 | 2013-04-23 |  | 0 | NOT STARTED |  |  |  | 0
t42 | Company search |  |  |  |  | 0 | STARTED |  |  |  | 0
|  | inhouse developers | 2013-03-16 | 2013-04-22
|  | Komal | 25 days
|  | kalyan | not yet given
SETUP

## Setup
Setup
| Category | Employee
| Category 1 | Employee 1
| Category 2 | Employee 2
| Category 3 | Employee 3
| Category 4 | Employee 4
Category 5
Category 6
PROJECTS